## Project Costs
Category | Estimated Cost (USD) | Actual Cost (USD)
Land Acquisition | 5000000 | 4500000
Construction | 15000000 | 14000000
Maintenance | 2000000 | 2100000
Utilities | 1000000 | 1200000
Other | 500000 | 400000

## Funding Sources
Source | Planned Funding (USD) | Received Funding (USD)
Government Grants | 8000000 | 8000000
Loans | 6000000 | 5500000
Public-Private Partnerships | 4000000 | 3500000
Tolls Revenue | 2000000 | 1800000

## Timeline
Milestone | Planned Date | Actual Date
Planning | 2024-01-01 | 2024-01-15
Land Acquisition | 2024-06-01 | 2024-07-01
Construction Start | 2024-12-01 | 2024-12-15
Construction Midpoint | 2025-06-01
Completion | 2026-01-01

## Performance Metrics
Metric | Value
Budget Utilization | 92
Schedule Adherence | 85
Cost Overrun (%) | 5
Funding Gap (%) | 10